## UseCases
ID | Description | Relevant requirements | Sitemap | Diagram | API REST
1 | Create an account | 1,1.1,1.2,1.3,1.4,1.4.1,12,13,14,14.1,21 | Completed | Completed | Completed
2 | Close an account | 4 | Completed | N/A | Completed
3 | View account balance | 18 | Completed | Completed | Completed
4 | View transactions | 5,5.1,18 | Completed | Completed | Completed
4.1 | Change transaction's notes | 21 | Completed | Completed | Completed
4.2 | Get a proof of transaction | 18 | Completed | N/A | N/A
5 | Transfer money | 15,17,18 | Completed | Completed | Completed
5.1 | Make a bank transfer | 9,9.1,9.2,15,17,18,19,21 | Completed | Completed | Completed
5.2 | Make a service payment | 6,6.1,6.2,15,17,18 | Completed | Completed | Completed
5.3 | Make a government payment | 7,7.1,15,17,18 | Completed | Completed | Completed
5.4 | Make a telco payment | 8,8.1,8.2,8.3,15,17,18 | Completed | Completed | Completed
6 | View scheduled transfers | 18 | Completed | Completed | Completed
6.1 | Schedule a transfer | 10,10.1,12,15,17,18 | Completed | Completed | Completed
6.2 | Change a scheduled transfer | 12,15,17,18 | Completed | N/A | Completed
6.3 | Delete a scheduled transfer | 18 | Completed | N/A | Completed
7 | View direct debits |  | Completed | Completed | Completed
7.1 | Toggle a direct debit |  | Completed | Completed | Completed
8 | View cards | 3,3.1,3.2,3.3 | Completed | Completed | Completed
8.1 | Toggle online payments |  | Completed | N/A | Completed
8.2 | Toggle NFC payments |  | Completed | N/A | Completed
8.3 | Change PIN | 20 | Completed | Completed | Completed
9 | Get documents |  | Completed | Completed | Completed
9.1 | Get IBAN proof | 2,2.1,19 | Completed | Completed | Completed
9.2 | Get account statements | 11,12,18 | Completed | Completed | Completed
10 | Change account information | 12,13,14,14.1,21 | Completed | Completed | Completed

## Requirements
ID | Description | Attachment | Use cases | Sitemap | Diagram | API REST
1 | The system shall allow the creation of accounts, using the attached data provided by the user. | 1. Email 2. Password 3. Full name 4. Birthday 5. Address 6. Tax number 7. ID number | 1 | Completed | Completed | Completed
1.1 | When creating an account, the system shall ensure the user is at least 18 years old. |  | 1 | N/A | N/A | N/A
1.2 | When creating an account, the system shall ensure the given email isn't already in use. |  | 1 | N/A | Completed | N/A
1.3 | When creating an account, the system shall store the account creation date and time. |  | 1 | N/A | Completed | N/A
1.4 | When creating an account, the system shall automatically create two debit cards, called "Physical Card" and "Virtual Card". |  | 1 | N/A | Completed | N/A
1.4.1 | When creating an account and its' respective cards, the cards should be valid for two years counting from their creation. |  | 1 | N/A | N/A | N/A
2 | The system shall be able to convert an account ID into the respective IBAN, using Banco de Portugal's specifications attached. | https://www.bportugal.pt/sites/default/files/anexos/documentos-relacionados/international_bank_account_number_vfinal_dpg_vr_20180226.pdf | 9.1 | N/A | N/A | N/A
2.1 | The system shall use "00972890" as the first digits of internal BBANs. |  | 9.1 | N/A | N/A | N/A
3 | The system shall be able to convert a card ID into the respective number. |  | 8 | N/A | Completed | N/A
3.1 | The system shall use "436339" as the first digits of all cards. |  | 8 | N/A | N/A | N/A
3.2 | The system shall use Luhn's formula to generate all cards' checksum, according to ISO/IEC 7812-1:2017. |  | 8 | N/A | N/A | N/A
3.3 | The system shall ensure all card numbers have exactly 16 digits. |  | 8 | N/A | Completed | N/A
4 | When closing an account, if the account's balance isn't 0, the system shall request an IBAN and transfer the remaining funds to the account that IBAN belongs to. |  | 2 | N/A | N/A | Completed
5 | The system shall allow filtering transactions by starting month, ending month, type (expense/income) and sender/receiver. |  | 4 | Completed | Completed | Completed
5.1 | The system shall ensure the starting month is less than or equal to the ending month. |  | 4 | N/A | N/A | N/A
6 | The system shall process service payments, with an entity, reference and amount provided by the user. |  | 5.2 | Completed | Completed | Completed
6.1 | The system shall ensure service entities have exactly 5 digits. |  | 5.2 | N/A | N/A | N/A
6.2 | The system shall ensure service references have exactly 9 digits. |  | 5.2 | N/A | N/A | N/A
7 | The system shall process government payments, with a reference and amount provided by the user. |  | 5.3 | Completed | Completed | Completed
7.1 | The system shall ensure government references have exactly 15 digits. |  | 5.3 | N/A | N/A | N/A
8 | The system shall process telco payments, with a provider, amount and phone number given by the user. |  | 5.4 | Completed | Completed | Completed
8.1 | The system shall ensure telco providers are in the attached data. | #NAME? | 5.4 | N/A | Completed | N/A
8.2 | The system shall ensure telco phone numbers have exactly 9 digits. |  | 5.4 | N/A | N/A | N/A
8.3 | The system shall ensure telco phone numbers start with 91, 92, 93 or 96. |  | 5.4 | N/A | N/A | N/A
9 | The system shall process bank transfers, with an IBAN, amount and optional note given by the user. |  | 5.1 | Completed | Completed | Completed
9.1 | If the IBAN in a bank transfer belongs to one of the bank's accounts, the system shall process the payment immediately, by creating the respective income transaction in the recepient's account. |  | 5.1 | N/A | N/A | N/A
9.2 | If the IBAN in a bank transfer belongs to an account outside the bank, the system shall use the respective external API to process the payment. |  | 5.1 | N/A | N/A | N/A
10 | The system shall allow scheduling transfers, given an IBAN, date, amount and frequency. |  | 6.1 | Completed | Completed | Completed
10.1 | The system shall allow the following values for scheduled transfers' frequency: Daily, weekly, monthly, yearly, applying the rules attached. | The system shall process all repeating transfers at midnight. If a transfer is repeated weekly, the system shall process the transfers exactly 7 days apart, on the same week day. If a transfer is repeated monthly, the system shall process the transfers on the same day of the month. If the day doesn't exist in a given month, the last day of the month shall be used instead. If a transfer is repeated yearly, the system shall process transfers on the exact same day, If the given day is the 29th of February and a given year isn't a leap year, the payment shall be processed on the 28th of February that year. | 6.1 | Completed | Completed | Completed
11 | The system shall generate monthly account statements. |  | 9.2 | Completed | N/A | N/A
12 | The system shall ensure all provided dates and datetimes are in conformity with the ISO 8601 standard. |  | 1,6.1,6.2,9.2,10 | N/A | N/A | N/A
13 | The system shall ensure all provided addresses are in conformity with the attached format. | - Address line 1 - Address line 2 (optional) - Postal code (####-###) - City - District | 1.1 | N/A | Completed | N/A
14 | The system shall ensure all provided tax numbers are in conformity with article 1 of "Decreto-Lei n.º 14/2013, de 28 de janeiro". | https://info.portaldasfinancas.gov.pt/pt/informacao_fiscal/legislacao/diplomas_legislativos/Documents/Decreto-Lei_14-2013.pdf | 1.1 | N/A | N/A | N/A
14.1 | The system shall use the procedure in 2.3.2 of the attached file to compute/verify the control number. | https://repositorio-aberto.up.pt/bitstream/10216/105401/2/200569.pdf | 1.1 | N/A | N/A | N/A
15 | The system shall prevent any transaction from being made in case it would result in the account's balance being below 0. |  | 5,5.1,5.2,5.3,5.4,6.1,6.2 | N/A | N/A | N/A
17 | For all transfers initiated by the user, the system shall ensure the amount is positive. |  | 5,5.1,5.2,5.3,5.4,6.1,6.2 | N/A | N/A | N/A
18 | The system shall use euros (€) for all currency and balance expressions. |  | 3,4,5,5.1,5.2,5.3,5.4,6,6.1,6.2,6.3,9.2,4.2 | N/A | N/A | N/A
19 | The system shall ensure all given IBANs conform to the ISO 13616 standard. |  | 5.1,9.1 | N/A | N/A | N/A
20 | The system shall ensure all given PINs have exactly 4 digits. |  | 8.3 | N/A | N/A | N/A
21 | The system shall ensure all user inserted strings do not exceed 80 characters, except where otherwise noted. |  | 1,4.1,5.1,10 | N/A | N/A | N/A

## Diagram ER
ID | Use Cases | Relevant requirements | Diagram | Use of tables
1 | Create an account | 1,1.1,1.2,1.3,1.4,1.4.1,12,13,14,14.1,21 | Completed | Account, Address, Cards
2 | Close an account | 4 | N/A | Account, Address, Cards, Transfers
3 | View account balance | 18 | Completed | Account
4 | View transactions | 5,5.1,18 | Completed | Transfers
4.1 | Change transaction's notes | 21 | Completed | Transfers
4.2 | Get a proof of transaction | 18 | Completed | Account, Transfers
5 | Transfer money | 15,17,18 | Completed | Account, Transfers
5.1 | Make a bank transfer | 9,9.1,9.2,15,17,18,19,21 | Completed | Account, Transfers
5.2 | Make a service payment | 6,6.1,6.2,15,17,18 | Completed | Account, Transfers
5.3 | Make a government payment | 7,7.1,15,17,18 | Completed | Account, Transfers
5.4 | Make a telco payment | 8,8.1,8.2,8.3,15,17,18 | Completed | Account, Transfers, TelcoProviders
6 | View scheduled transfers | 18 | Completed | Account, StandingOrder
6.1 | Schedule a transfer | 10,10.1,12,15,17,18 | Completed | Account, StandingOrder
6.2 | Change a scheduled transfer | 12,15,17,18 | N/A | Account, StandingOrder
6.3 | Delete a scheduled transfer | 18 | N/A | Account, StandingOrder
7 | View direct debits |  | Completed | Account, DirectDebit
7.1 | Toggle a direct debit |  | Completed | Account, DirectDebit
8 | View cards | 3,3.1,3.2,3.3 | Completed | Account, Cards
8.1 | Toggle online payments |  | N/A | Account, Cards
8.2 | Toggle NFC payments |  | N/A | Account, Cards
8.3 | Change PIN | 20 | Completed | Account, Cards
9 | Get documents |  | Completed | Account
9.1 | Get IBAN proof | 2,2.1,19 | Completed | Account
9.2 | Get account statements | 11,12,18 | Completed | Account
10 | Change account information | 12,13,14,14.1,21 | Completed | Account

## Sitemap
ID | Description | Relevant requirements | Sitemap status | Use of Pages
1 | Create an account | 1,1.1,1.2,1.3,1.4,1.4.1,12,13,14,14.1,21 | Completed | 1. Login/Register -> 2.Create account
2 | Close an account | 4 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Delete Account
3 | View account balance | 18 | Completed | 1. Login/Register -> 2.Overview (Balance)
4 | View transactions | 5,5.1,18 | Completed | 1. Login/Register -> 2.Overview (View Transactions) -> 3.List of Transactions
4.1 | Change transaction's notes | 21 | Completed | 1. Login/Register -> 2.Overview (View Transactions) -> 3.List of Transactions(select) -> 4.Change Transaction Note
4.2 | Get a proof of transaction | 18 | Completed | 1. Login/Register -> 2.Overview (View Transactions) -> 3.List of Transactions(select) -> 4.Download proof of transaction
5 | Transfer money | 15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer
5.1 | Make a bank transfer | 9,9.1,9.2,15,17,18,19,21 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer -> 4. IBAN Transfer
5.2 | Make a service payment | 6,6.1,6.2,15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Service Payment
5.3 | Make a government payment | 7,7.1,15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Service Payment -> 4. Payment to the Government
5.4 | Make a telco payment | 8,8.1,8.2,8.3,15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Service Payment -> 4.TELCO Payments
6 | View scheduled transfers | 18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer -> 4. Standing Order -> 5. View Standing Orders
6.1 | Schedule a transfer | 10,10.1,12,15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer -> 4. Standing Order -> 5. Create Standing Order
6.2 | Change a scheduled transfer | 12,15,17,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer -> 4. Standing Order -> 5. Change Standing Order
6.3 | Delete a scheduled transfer | 18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Money Transfer -> 4. Standing Order -> 5. Delete Standing Order
7 | View direct debits |  | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Direct Debit -> 4.List of Direct Debit
7.1 | Toggle a direct debit |  | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Direct Debit -> 4.Toggle Direct Debit
8 | View cards | 3,3.1,3.2,3.3 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Card Manager -> 4. List of Cards
8.1 | Toggle online payments |  | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Card Manager(select) -> 4. Toggle Online Payment
8.2 | Toggle NFC payments |  | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Card Manager(select) -> 4. Toggle NFC Payment
8.3 | Change PIN | 20 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Card Manager(select) -> 4. Change PIN
9 | Get documents |  | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Bank Assistant -> 4. Documents
9.1 | Get IBAN proof | 2,2.1,19 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Bank Assistant -> 4. Documents -> 5. Get IBAN Proof
9.2 | Get account statements | 11,12,18 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Bank Assistant -> 4. Documents -> 5.Account Statement
10 | Change account information | 12,13,14,14.1,21 | Completed | 1. Login/Register -> 2.Overview (Account Mng) -> 3.Bank Assistant -> 4. Change Account Information

## API REST
ID | Description | Relevant requirements | API REST
1 | Create an account | 1,1.1,1.2,1.3,1.4,1.4.1,12,13,14,14.1,21 | Completed
2 | Close an account | 4 | N/A
3 | View account balance | 18 | N/A
4 | View transactions | 5,5.1,18 | N/A
4.1 | Change transaction's notes | 21 | N/A
4.2 | Get a proof of transaction | 18 | N/A
5 | Transfer money | 15,17,18 | N/A
5.1 | Make a bank transfer | 9,9.1,9.2,15,17,18,19,21 | N/A
5.2 | Make a service payment | 6,6.1,6.2,15,17,18 | N/A
5.3 | Make a government payment | 7,7.1,15,17,18 | N/A
5.4 | Make a telco payment | 8,8.1,8.2,8.3,15,17,18 | N/A
6 | View scheduled transfers | 18 | N/A
6.1 | Schedule a transfer | 10,10.1,12,15,17,18 | Completed
6.2 | Change a scheduled transfer | 12,15,17,18 | Completed
6.3 | Delete a scheduled transfer | 18 | N/A
7 | View direct debits |  | Completed
7.1 | Toggle a direct debit |  | N/A
8 | View cards | 3,3.1,3.2,3.3 | N/A
8.1 | Toggle online payments |  | Completed
8.2 | Toggle NFC payments |  | N/A
8.3 | Change PIN | 20 | Completed
9 | Get documents |  | N/A
9.1 | Get IBAN proof | 2,2.1,19 | N/A
9.2 | Get account statements | 11,12,18 | N/A
10 | Change account information | 12,13,14,14.1,21 | Completed
N/A
N/A
Completed
Completed
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A

## Local (hidden)
Status
Completed
Not completed
In progress
N/A